## Slide 1
CLARA Application Development
Sprints 1 & 2

## Slide 2
S.No | Developments | Remarks
1 | API Integration – Mozeo | Development
2 | Data Modelling Design | Includes Data Modelling for Setup All Modules of L&E and Immigration process
3 | UI/UX – CRM Screens Design Inquiry Potential Client Intake Forms Conflict Check Potential Client Agreement Client Creation | Includes Screens Design for Potential Client Intake Form development for 6 forms (English & Spanish) Analysis and segregation of Office Use fields in each form
4 | Functional Specification Setup CRM | Includes Functional Specification for 35 Setup Functionalities 15 Workflow processes in CRM
Sprint 1 (31 Aug 2021 - 20 Sep 2021)

## Slide 3
S.No | Developments | Remarks
5 | Table Structure Creation Setup CRM | Includes tables structure creation for Setup - 35 Nos CRM - 10 Nos Development of all setup functionalities are included in this sprint considering the dependency with other modules (earlier Sprint proposal covered only the development of CRM setup in Sprint 1 & Sprint 2)
6 | Microservices Development CRM Inquiry Forms | 
7 | API Integration with Angular CRM Inquiry Forms | Development, UI Validations, Data Binding, Consume APIs in Angular Framework
8 | API Development for Website’s (M&R) WordPress DB integration | To provide APIs to vendor team (Danny) to push the data from website DB to Clara DB
Sprint 1 (31 Aug 2021 - 20 Sep 2021)

## Slide 4
S.No | Developments | Remarks
1 | API integration – DocuSign | Development
2 | UI/UX – Screens Design Setup | Includes Screens Design for Setup (35 Nos) Development of all setup functionalities are included in this sprint considering the dependency with other modules (earlier Sprint proposal covered only the development of CRM setup in Sprint 1 & Sprint 2)
3 | Microservices Development Potential client Agreement Conflict Check Client creation Configuration | 
4 | Document Storage Development | 
Sprint 2 (21 Sep 2021 - 18 Oct 2021)

## Slide 5
S.No | Developments | Remarks
5 | API Integration with Angular Potential client Agreement Conflict Check Client creation Configuration | Development, UI Validations, Data Binding, Consume APIs in Angular Framework
6 | Mail Merge Functionality | Includes development of Mail merge functionality for 1 No. Agreement Document Mail Merge Components Development
7 | Mozeo API (Integration) | Integration with CLARA and internal testing (Need to have a US mobile no from Client to test the SMS integration)
8 | DocuSign API (Integration) | Integration with CLARA and internal testing
Sprint 2 (21 Sep 2021 - 18 Oct 2021)

## Slide 6
S.No | Developments | Remarks
9 | Website API Integration | API integration with CLARA and testing
10 | CRM – Reports Development | Includes CRM Reports (3 Nos) Reports Screen Design API Development and Integration
11 | Unit Testing (Internal) Bug Fixes Integration Testing | Includes testing for Setup CRM – End to End workflow Integration with Mozeo Integration with DocuSign Intake Form Email Notifications to Clients Bugs fixing
Note :
Client Portal and Client Management have been moved to subsequent sprints since there is a dependency with other modules.
Sprint 2 (21 Sep 2021 - 18 Oct 2021)