## MVP
S.NO | Module | Module Type | Sub Module | DB insert | Display | Data flow(CRUD) | Boostrap UI | React UI | Microservices - CRUD | DB Script | MS Review Status
1 | Login | Login Setup | SignIn | ü | ü | ü | ü
|  | Login Setup | Change Password | ü | ü | ü
2 | User Management | Configuration | Role Access Management |  |  | ü
|  |  | User Creation |  |  | ü
3 | Landing page | Landing page | Landing page |  | ü | ü
4 | Enterprise Setup | Configuration | Adhoc Module | ü |  |  |  |  | ü | ü | Reviewed
|  |  | Company |  |  | ü | ü |  | ü | ü | Reviewed
|  |  | Plant | ü |  | ü | ü |  | ü | ü | Reviewed
|  |  | Warehouse |  |  | ü | ü |  | ü | ü | Reviewed
|  |  | Floor |  |  | ü | ü |  | ü | ü | Reviewed
|  |  | Storage Section |  |  | ü | ü |  | ü | ü | Reviewed
|  |  | Storage Class |  | ü |  |  |  | ü | ü | Reviewed
|  |  | Storage Type |  | ü |  |  |  | ü | ü | Reviewed
|  |  | Storage Bin type |  | ü |  |  |  | ü | ü | Reviewed
|  |  | Item Type | ü |  |  |  |  | ü | ü | Reviewed
|  |  | Item Group | ü |  |  |  |  | ü | ü | Reviewed
|  |  | Item Sub Group | ü |  |  |  |  | ü | ü | Reviewed
|  |  | Batch Serial Mangement | ü |  |  |  |  | ü | ü | Reviewed
|  |  | Variant Management |  | ü |  |  |  | ü | ü | Reviewed
|  |  | Strategies |  |  | ü |  |  | ü | ü | Reviewed
|  |  | Employee | [5 empty] | ü | ü | Reviewed
|  |  | Doors | [5 empty] | ü | ü | Reviewed
|  |  | Barcode Management |  | ü |  |  |  | ü | ü | Reviewed
5 | Masters | Masters | Item Master |  | ü |  | In progress |  | ü | ü | Not reviewed
|  |  | Storage Bin |  | ü |  |  |  | ü | ü | Not reviewed
|  |  | Handling Equipment | ü |  |  |  |  | ü | ü | Not reviewed
|  |  | Handling Unit | ü |  |  |  |  | ü | ü | Not reviewed
|  |  | Customer | ü |  |  |  |  | ü | ü | Not reviewed
|  |  | BOM - Kitting | [5 empty] | ü | ü | Not reviewed
|  |  | Vendor | ü |  |  |  |  | ü | ü | Not reviewed
|  |  | Dock | [5 empty] | ü | ü | Not reviewed
|  |  | Work Center | [5 empty] | ü | ü | Not reviewed
|  |  | Cycle Count Scheduler | [5 empty] | ü | ü | Not reviewed
6 | Pre Inbound Operations | Transactions | Pre inbound Creation |  |  | ü |  |  | Dev Partially completed |  | Not reviewed
|  |  | Receipt Planning | [5 empty] | Dev Partially completed |  | Not reviewed
|  |  | Dock planning | [5 empty] | Dev Partially completed |  | Not reviewed
|  |  | Inbound integration Log | [5 empty] | Dev Partially completed |  | Not reviewed
7 | Inbound Operations | Transactions | Dock Management | [5 empty] | Dev Partially completed |  | Not reviewed
|  |  | Conatiner receipt |  |  | ü |  |  | Dev Partially completed |  | Not reviewed
|  |  | Goods receipt |  |  | ü |  |  | Dev Partially completed |  | Not reviewed
|  |  | Putaway |  |  | ü |  |  | Dev Partially completed |  | Not reviewed
|  |  | Inbound Confirmation |  |  | ü |  |  | Dev Partially completed |  | Not reviewed
|  |  | Reversals | [5 empty] | Dev Partially completed |  | Not reviewed
8 | Transfers | Transactions | Warehouse to Warehouse transfers |  |  | ü
|  |  | Inhouse transfers |  |  | ü
Scrapping
|  |  | Block - Item |  | ü
|  |  | Block- Storage Bin |  | ü
9 | Preoutbound operations | Transactions | Pre Outbound Creation |  |  | ü
reservations
Outbound Integration log
10 | Outbound Operations | Transactions | Orders Allocation |  |  | ü
|  |  | Picking |  |  | ü
|  |  | Quality |  |  | ü
Packing
|  |  | Delivery Confirmation |  |  | ü
|  |  | Cross Docking - Creation |  |  | ü
|  |  | Cross Docking - Confirmation |  |  | ü
11 | Returns | Transactions | Return orders creation
12 | Cycle Count | Transactions | Cycle Count Creation |  |  | ü
|  |  | Cycle Count Confirmation |  |  | ü
13 | Analytics | Dashboard | Warehouse Structure |  |  | ü
|  |  | Inbound performance |  | ü
|  |  | Shipment performance |  | ü
|  | Report | Utilisation |  | ü
|  |  | Fulfillment |  | ü
|  |  | Inventory levels |  | ü
|  |  | Ageing |  | ü
|  |  | Productivity |  | ü
|  |  | Ontime Delviery |  | ü
|  |  | Cycle Count |  | ü
14 | Masters | ID Master | vertical id | ü
|  |  | company id | ü
|  |  | warehouse id | ü
|  |  | plant id | ü
|  |  | floor id | ü
|  |  | storage section id | ü
|  |  | row id | ü
|  |  | aisle id | ü
|  |  | span id | ü
|  |  | shelf id | ü
|  |  | storage class id | ü
|  |  | stroage type id | ü
|  |  | storage bin type id | ü
|  |  | door id | ü
|  |  | process_id | ü
|  |  | user type id | ü
|  |  | language id | ü
|  |  | uom id | ü
|  |  | module id | ü
|  |  | adhoc module id | ü
|  |  | level id | ü
|  |  | palletization level id | ü
|  |  | approval process id | ü
|  |  | currency_id | ü
|  |  | barcode subtype id | ü
|  |  | barcode type id | ü
|  |  | employee id | ü
|  |  | strategy id | ü
|  |  | menu id | ü
|  |  | bin section id | ü
|  |  | date format id | ü
|  |  | decimal notation id | ü
|  |  | status messages id | ü
|  |  | warehouse type id | ü
|  |  | movement type id | ü
|  |  | sub movement type id | ü
|  |  | transfer type id | ü
|  |  | stock type id | ü
|  |  | special stock indicator id | ü
|  |  | handling_equipment_id | ü
|  |  | handling_unit_id | ü
|  |  | dock_id | ü
|  |  | work_ center_id | ü
|  |  | cyclecount type id | ü
|  |  | return type id | ü
|  |  | outbound order type id | ü
|  |  | outbound order status id | ü
|  |  | inbound order type id | ü
|  |  | inbound order status id | ü
|  |  | bin class id | ü
|  |  | block type id | ü
|  |  | approval id | ü
|  |  | country id | ü
|  |  | state id | ü
|  |  | city id | ü

## Microservice API Details
Module | Module Type | Sub Module | Microservices
Login | Login Setup | SignIn
| Login Setup | Change Password
User Management | Configuration | Role Access Management
User Creation
Landing page | Landing page | Landing page
Enterprise Setup | Configuration | Adhoc Module
Company
Plant
Warehouse
Floor
Storage Section
Storage Class
Storage Type
Storage Bin type
Item Type
Item Group
Item Sub Group
Batch Serial Mangement
Variant Management
Strategies
Employee
Doors
Barcode Management
Masters | Masters | Item Master
Storage Bin
Handling Equipment
Handling Unit
Customer
BOM - Kitting
Vendor
Dock
Work Center
Cycle Count Scheduler
Pre Inbound Operations | Transactions | Pre inbound Creation
Receipt Planning
Dock planning
Inbound integration Log
Inbound Operations | Transactions | Dock Management
Conatiner receipt
Goods receipt
Putaway
Inbound Confirmation
Reversals
Transfers | Transactions | Warehouse to Warehouse transfers
Inhouse transfers
Scrapping
Block - Item
Block- Storage Bin
Preoutbound operations | Transactions | Pre Outbound Creation
reservations
Outbound Integration log
Outbound Operations | Transactions | Orders Allocation
Picking
Quality
Packing
Delivery Confirmation
Cross Docking - Creation
Cross Docking - Confirmation
Returns | Transactions | Return orders creation
Cycle Count | Transactions | Cycle Count Creation
Cycle Count Confirmation
Analytics | Dashboard | Warehouse Structure
Inbound performance
Shipment performance
| Report | Utilisation
Fulfillment
Inventory levels
Ageing
Productivity
Ontime Delviery
Cycle Count
Masters | ID Master | vertical id
company id
warehouse id
plant id
floor id
storage section id
row id
aisle id
span id
shelf id
storage class id
stroage type id
storage bin type id
door id
process_id
user type id
language id
uom id
module id
adhoc module id
level id
palletization level id
approval process id
currency_id
barcode subtype id
barcode type id
employee id
strategy id
menu id
bin section id
date format id
decimal notation id
status messages id
warehouse type id
movement type id
sub movement type id
transfer type id
stock type id
special stock indicator id
handling_equipment_id
handling_unit_id
dock_id
work_ center_id
cyclecount type id
return type id
outbound order type id
outbound order status id
inbound order type id
inbound order status id
bin class id
block type id
approval id
country id
state id
city id