## Classic WMS
Product: 5PL Suite, Module: Classic WMS
WBS/Sno | Product Tasks | Task Type | Assigned to | Effort | Duration | Resource Monthly Cost |  |  | Other Cost |  |  | Budget | Actuals | Balance Under/Over
|  |  |  | Duration |  | Planned | Actuals | Cost Per Month | Infra Per Month | Others 1 | Others 2
1 | Enterprise Setup | Microservices | Devi | 4 weeks | 1-4 weeks |  |  | 75000 | 5000 |  |  | 80000 | 5000 | 75000
|  | DB Script | Devi | 2 weeks
|  | React JS | Jagan | 4 weeks
|  | Integration | Devi & Jagan | 2 weeks
|  | Functional | Raj | 1 week
|  | Boostrap UI | Mugilan | 1 week
2 | Login & User Management | Microservices | Devi | 1 week |  |  |  | 0 |  |  |  | 75000 | 0 | 75000
|  | DB Script | Devi
|  | React JS | Jagan | 1 week
|  | Integration | Devi & Jagan | 1 week
|  | Functional | Raj | 0
|  | Boostrap UI | Mugilan | 0
3 | ID Master | DB Script | Devi | 2 weeks | 2 weeks
3 | Masters | Microservices | Arun | 1 week | 5-7 weeks | 1 | 1 | [5 empty] | 0 | 0
|  | DB Script | Devi | 1 week
|  | React JS | Jagan | 2-3 weeks |  | 1 | 0
|  | Integration | Arun & Jagan | 2 weeks |  | 0.5 | 0
|  | Functional | Raj | 1 week |  | 1 | 1
|  | Boostrap UI | Mugilan | 1 week |  | 1 | 1
4 | Pre Inbound Operations | Microservices | Devi | 2 weeks | 1-4 weeks | 1 | 0 | [5 empty] | 0 | 0
|  | React JS | Jagan | 1 week |  | 1 | 0
|  | Integration | Arun & Jagan | 1 week |  | 0.5 | 0
|  | Functional | Raj | 1 week |  | 1 | 1
|  | Boostrap UI | Mugilan | 1 week |  | 1 | 1
5 | Inbound Operations | Microservices | Devi | 3 weeks | [8 empty] | 0 | 0
|  | React JS | Jagan | 2 weeks
|  | Integration | Arun & Jagan | 1 week
|  | Functional | Raj | 1 week
|  | Boostrap UI | Mugilan | 1 week
6 | Transfers | Microservices | Arun | 2 weeks | 3-4 weeks | [7 empty] | 0 | 0
|  | React JS | XXX | 3 weeks
|  | Integration | Arun & Jagan | 2 weeks
|  | Functional | Raj | 1 week
|  | Boostrap UI | Mugilan | 1 week
7 | Pre Outbound Operations | Microservices | Arun |  | 1-4 weeks | [7 empty] | 0 | 0
|  | React JS | XXX
|  | Integration | Arun & Jagan
|  | Functional | Raj
|  | Boostrap UI | Mugilan
8 | Outbound Operations | Microservices | Arun | [9 empty] | 0 | 0
|  | React JS | XXX
|  | Integration | Arun & Jagan
|  | Functional | Raj
|  | Boostrap UI | Mugilan
9 | Returns |  |  |  | 2 weeks | [7 empty] | 0 | 0
10 | Cycle Count | [11 empty] | 0 | 0
11 | Dashboard/Reports |  |  |  | 2 weeks | [7 empty] | 0 | 0
12 | Android Mobile App |  |  |  | 6-8 weeks | [7 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
Sub Total | [11 empty] | 155000 | 5000 | 150000

## Costing
Modules | Devi | Arun | Jagan | React JS Dev2 | Mobile App Dev1
Enterprise Setup | 50000 |  | 75000
Login & User Management
Masters |  | 50000 |  | 75000
Cycle Count UI work
Pre Inbound Operations | 75000 |  | 75000
Inbound Operations
Pre Outbound Operations |  | 75000 |  | 75000
Outbound Operations
Transfers | 75000 |  | 75000
Returns
Cycle Count |  | 75000
Dashboard/Reports |  |  |  | 75000
Android Mobile App |  |  |  |  | 200000
Resourcewise Cost | 200000 | 200000 | 225000 | 225000 | 200000
Consumed Cost | 100000
Product Cost | 1050000
20% Buffer (Additional) | 210000
Final Product Cost | 1360000