## Flourish B2B API Dev
Project Start Date | 2021-01-18 | This can be changed
Project End Date (Forecast)
WMS MVP1 Development Plan
Activities Planned | # of Man Days | Target Date | Resource | OneTime Setup | Status | Milestone | Remarks | Assumption/Dependencies
Environment setup on workstations | 0 | 2021-01-18 | Muru & Team | Yes | Completed
Requirements - Queries & Clarifications | 0 | 2021-01-18 | Raj & Team | -- | In Progress |  | Ongoing Activity
WMS - MVP1 Design & discussions | 5 | 2021-01-23 | Muru & Team | Yes | In Progress | M1 | Ongoing Activity
Database table script development | 90 | 2021-04-18 | Dev1 | -- | In Progress
ID Master - Table script development - 55 Tables | 4 |  |  | --
Enterprise Setup - 19 Tables | 2
User Management, Masters, Pre Inbound & Inbound Operations - 22 Tables | 3
Rest of the modules - 28 Tables | 3
Basic Spring boot setup and configuraions | 2
DAO and JPA setup and configurations | 2
OAUTH Integration | 3 | 2021-01-21 | Dev1 |  | Open |  | Will be reusable from Flourish
Enterprise Setup Development |  |  | Dev2
CRUD Development
Company | 5
Plant | 3
Warehouse | 3
Floor | 3
Storage Section | 3
User Management
CRUD Development
Role Access Management | 3 |  | Dev1
User Creation | 3
Pre Inbound Operations |  |  | Dev2
CRUD Development
Pre inbound Creation | 3
Inbound Operations |  |  | Dev1
CRUD Development
Conatiner receipt | 3
Goods receipt | 3
Putaway | 3
Inbound Confirmation | 3
Transfers |  |  | Dev2
CRUD Development
Warehouse to Warehouse transfers | 3
Inhouse transfers | 3
Preoutbound operations |  |  | Dev1
CRUD Development
Pre Outbound Creation | 3
Outbound Operations |  |  | Dev2
CRUD Development
Orders Allocation | 3
Picking | 3
Quality | 3
Delivery Confirmation | 3
Cross Docking - Creation | 3
Cross Docking - Confirmation | 3
Cycle Count |  |  | Dev1
CRUD Development
Cycle Count Creation | 3
Cycle Count Confirmation | 3