## Classic WMS
S.No | Ticket No. | Submitted | Issue Description | Type | Issue Date | Priority | Root Cause / Solution Details | Status | Closed Date | Last Comments | Consultant
1 | CWMS/IW/2022/001 | Noufal | INVENTORY QUANTITY - 110 QTY INCREASED - SKU 020307402 | Repeat | 2022-05-09 |  | Received Multiple requests from UI for Putaway confirmation. Fixed to handle the multiple requests | Closed | 2022-08-09 | We had put a technical fix for the below issue and adjusted the inventory qty as per the physical stock | Raj
2 | CWMS/IW/2022/002 | Noufal | Quality status not updated after delivery confirmation | New | 2022-08-09 |  |  | Open |  |  | Raj
3 | CWMS/IW/2022/003 | Ahad | System and Device slow | Repeat | 2022-08-09 |  |  | In Progress |  | Fixed Performance issues in HHT for Quality and Putaway. Working on others | Raj
4 | CWMS/IW/2022/004 | Jineesh | Perpetual - Unable to run - Outbound Error message popped up | New | 2022-10-09 |  |  | Open |  |  | Raj
5 | CWMS/IW/2022/005 | Noufal | Multiple Status for same TOs in different tab - TO-063537 | Repeat | 2022-10-09 |  | Error thrown when updating pickup lines as records were multiple. Fixed to handle multiple pickup lines | Fixed |  | Updated old orders. Future orders to be monitored | Raj
6 | CWMS/IW/2022/006 | Noufal | Auto Filter/Search parameter need to remove from delivered tab | New | 2022-10-09 |  | Removed as requested | Fixed |  |  | Raj
7 | CWMS/IW/2022/007 | Jineesh | incorrect allocation strategy | New | 2022-10-09 |  | Detailed the adopted strategy in E mail. Stratey by FIFO(Pallet ID ) is not feasible as there are different types of pallet ID numbers being used | Closed |  | Allocation strategy via existing Pallet ID number range combination is technically not feasible | Raj
8 | CWMS/IW/2022/008 | Noufal | TO-063427 Customer Posted, Not created in our system | Repeat | 2022-11-09 |  | TO Pushed from Back end. Analysing the RC | closed |  | TO Pushed from back end, Root cause analyse will be done and updated soon | Raj
9 | CWMS/IW/2022/009 | Noufal | Picked and QC quantity difference (Portal Picking) | Repeat | 2022-11-09 |  | Could not simulate the issue. Need more details | Open |  | Can't Simulate this issue. Waiting for re-occurnace to find the root cause | Raj
10 | CWMS/IW/2022/010 | Noufal | Reversal Not working | Repeat | 2022-11-09 |  | Error thrown when updating pickup lines as records were multiple. Fixed to handle multiple pickup lines | Fixed |  |  | Raj
11 | CWMS/IW/2022/011 | Anwar | ASN 760 SKU#0203011053 quantity mismatch | Repeat | 2022-11-09 |  | Received Multiple requests from UI for Putaway confirmation. Fixed to handle the multiple requests | Fixed |  |  | Raj
12 | CWMS/IW/2022/012 | Noufal | Transfer order which returned with bad request error message. (TO#:063386); customer is not able to receive their showroom orders for the upcoming SALE starting next week | Repeat | 2022-12-09 |  |  | In Progress |  | Awaiting for Customer to share the log file. | Raj
13 | CWMS/IW/2022/013 | Jineesh | Quantity mismatch in Inventory Data | Repeat | 2022-09-12 |  |  | In Progress |  | Analysis is in Progress | Raj
14 | CWMS/IW/2022/014 | Noufal | Physical Received – 18 QTY; In RC - 19QTY; Order No. ASN000000769 | Repeat | 19/9/2022 |  |  | Fixed |  | Qty Adjusted. Released new Apk version in HHT with fix | Raj
15 | CWMS/IW/2022/015 | Noufal | Multiple Status for same ASN/Return TO | New | 20/9/2022 |  |  | In Progress |  |  | Pandiyan
16 | CWMS/IW/2022/016 | Noufal | not able to pick from multiple locations, partially allocated items facing this issue | New | 20/9/2022 |  | confirmation was done in HHT and failed to update one of tables at the back end | Fixed |  | Issue was fixed and deployed | Raj
17 | CWMS/IW/2022/017 | Noufal | item inventory showing is allocated 1 but order showing is allocated 3 Qyt | Repeat | 26/9/2022 |  |  | In Progress |  |  | Raj
18 | CWMS/IW/2022/018 | Noufal | quantity mismatch between Order-Picked-QA-Delivery Quantities | New | 28/9/2022 |  |  | In Progress |  |  | Pandiyan
19 | CWMS/IW/2022/019 | Noufal | Error message popped up while doing allocation – Order Management | New | 29/9/2022 |  |  | In Progress |  |  | Pandiyan
20 | CWMS/IW/2022/020 | Noufal | Picker picked by adding bin from another location. The first allocated ID still showing as allocated even after completed confirmation of TO | New | 29/9/2022 |  |  | In Progress |  |  | Pandiyan