## Sheet1
S.No | Process | Points | Priority | Links | Status | Remarks | status as on 03/04/22
1 | Preinbound | InboundordertypeID value to be inserted in Preinboundline | high |  | Fixed |  | Fixed
2 | Preinbound | Prenibound header and line not inserted for Warehouse ID 111 through AX integration | High |  | Fixed |  | Fixed
3 | Preinbound | BOM Child Item Not inserted in Preinboundline table | High |  | Fixed |  | Fixed
4 | Preinbound | Insert BOM API not inserting records Preinboundline table. Add BOM item -for muliptle records | High |  | Open | Raj will tets and come back | Fixed
5 | Case Receipt | Status ID of STAGINGHEADER and INBOUNDLINE updated as 14 when all records of STATGINGLINE are not updated as 14 | Medium |  | Fixed |  | Fixed
6 | Goods Receipt | StatusID of STAGINGLINE update as 17 to include CASE_CODE when looking for record | High |  | Fixed |  | Fixed
7 | Goods Receipt | Bin Determination is always proposing STAGING Bin, but bins are available for condition 1 and 2 | High |  | Open | Raj will tets and come back | Fixed
8 | Goods Receipt | Accepted qty and damaged quantities are not updated properly. | High |  | Fixed |  | Fixed
9 | Inbound Confirmation | Additional validation required before confirmation | Medium |  | Open |  | Open
10 | Reversal | Reversal condition addition | High |  | Open | Raj will tets and come back | Open
11 | Reversal | Remove the below status updates 1. Pass the selected REF_DOC_NO/PACK_BARCODE/CASE_CODE values in GRLINE table GRHEADER tables and update Status ID as 16 2. Pass the selected REF_DOC_NO/IB_LINE_NO values in INBOUNDLINE tables and update Status ID as 13 | Medium |  | Fixed |  | Fixed
12 | Inbound Confirmation | Remove below status update after Inbound confirmation PUTAWAY table STATUS Updates Pass WH_ID/PRE_IB_NO/REF_DOC_NO/IB_LINE_NO/ITM_CODE values in PUTAWAYLINE tables and update STATUS_ID as 24 Pass WH_ID/PRE_IB_NO/REF_DOC_NO values in PUTAWAYHEADER tables and update STATUS_ID as 24 | Medium |  | Fixed |  | Fixed
13 | IMBASICDATA | Get IMBasic Data API is not having Item code as input | Low |  | Fixed |  | Fixed
14 | Integration | Other than ASN api, no API insert a record in PREINBOUND tables | High |  | Fixed |  | Fixed
15 | Storage Bin | Status ID to be included in Search Apis | Medium |  | Fixed |  | Open
16 | Inventory | Bin Class ID to be included in Search APIs | Medium |  | Fixed |  | Open
17 | Storage Bin | BOM Number is not autogenerated and asking for Input from UI | High |  | Fixed |  | Fixed
18 | Preinbound | new item is added in preinbound line which was not sent in integration API | High |  | Fixed |  | Fixed
19 | Inhouse transfer | Bin to Bin transfer - Error response | high |  | Fixed |  | Fixed
20 | User Mgt | E mail ID is unique in User Mgt and Get ALL Usewr mgt API is missing | Medium |  | Fixed |  | Fixed
21 | Staging Line | Deletion indicator 1 records are fetched in Find Staging Line | Medium |  | Fixed |  | Fixed
22 | Replace ASN | Eror message in replace ASN | Medium |  | Open | Raj will tets and come back | Fixed
23 | ordermanagement | Inventory Qty is not updated in Ordermanagementline creation | high |  | Open
24 | ordermanagement | Proposed StorageBin to be filled in Ordermanagement line once allocated | high |  | Open
25 | Picking | AddBIn should exclude proposed storage bin | high |  | Open
26 | Preinbound | Expected Arrival date is coming as 1 day before | high |  | Open
27 | Picking | No body error in Picking line confirmation API | high |  | Open
28 | Outboundline | Outboundline confirmation API to be modified | high |  | Open

## Sheet2
Point No
9
10

## Sheet3
ID masters
Status ID
Item type ID
Item group ID
Floor ID
Level ID
Hard coded values | Hard coded values
Inbound order type | Outbound order type
1 - ASN | 0 - SO
2 - Store Return | 1-WH2WH
3 - WH2WH | 2- Return PO
4 - Saleorder return | 3- TE Order